## Sheet1
Third Year Group Project
Week | Student Group | Client | Supervisor (based in EEE Dept)
2021-02-14 |  | submit project proposal to c.drysdale@imperial.ac.uk
2021-02-28
submit 5 slide presentation/video for client pitch to students to c.drysdale@imperial.ac.uk
2021-03-08 |  | invited to attend presentation to students (5 slides/video) describing project and 'pitching' for group to work on it. Q&A session available.
Project
Week -1 | contact client to arrange briefing meting in Week 1
Week 0
Week 1 - 26 Apr 21 | Meet with Client for full briefing on project, context and expectations. Write single page A4 summary of meeting for discussion with IC supervisor. Attend Team building workshop. | Meet with students to brief on project, expectations and any relevant contextual information, available resources etc.
Week 2 | Clarify leaflet with client and supervisor and plan of work, justification of approach and proposed solutions | Sanity check leaflet with students and provide feedback. Arrange site visit | Meet with students to discuss project, explore ideas for approaching project. Check on progress of work and delivery of leaflet.
Week 3 |  |  | provide group with technical support and mentoring
Week 4
Week 5 | produce draft flyer for supervisor/client | invited to provide formative feedback on flyer | formative feedback on flyer
Week 6 - Fri 4 June | Groups submit 2pp A 4 flyer; attend
Week 7 -Thurs 17 June pm | Hackbooth Demonstration and poster presentation | Attend hackbooth demonstration and poster presentation | Attend hackbooth demonstration and poster presentation
Week 8
Week 9 - 24 June | submission of documentation and peer assessment | Provide feedback on documentation and group's performance. | Review and mark documentation and provide overall mark for peoject